## Schedule
PROJECT TITLE: Data Release 46
[6 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-10-25 |  | Goal/Milestone: Use 1 for Days Req |  |  |  | October | [6 empty] | November | [34 empty] | December
Scrolling Increment: | 0 | time axis 2022-10-25 to 2022-12-19
Milestone description | Category | Assigned to | Progress | Start | 1 Day Before Due Date | Days Req | time axis 2022-10-25 to 2022-12-19
Update Reagents DR45
Update reagent mapping in code | On Track | Alex | 100% | 2022-10-19 | 2022-10-22 | 3
Run code with fixed reagnet mapping | High Risk | Alex | 94% | 2022-10-22 | 2022-10-27 | 5
Have Curation team do a QA and QC of reagent update spreadsheet | Med Risk | David / Renuka | 0% | 2022-10-27 | 2022-11-05 | 9
Send Henry Reagent Spreadsheet | Low Risk | Alex | 0% | 2022-10-30 | 2022-11-10 | 11
Edit Json script and implement
Edit Json script and implement | High Risk | Alex | 0% | 2022-10-24 | 2022-10-31 | 7
Update new studies (n=20)
Review study files for having all the data. | Low Risk | David / Renuka / Alex | 100% | 2022-10-19 | 2022-11-15 | 27
Extract from paper or ask POC as needed. | High Risk | David / Renuka / Alex | 0% | 2022-10-19 | 2022-11-15 | 27
Rename files / Add insightful descriptors for each file in the SeroNet Registary template | Low Risk | David / Renuka / Alex | 0% | 2022-10-25 | 2022-11-15 | 21
Update previous (pre-DR45) studies that are missing supporting files (n=10)
Indentify issues in Studies | Milestone | Elaine | 100% | 2022-10-19 | 2022-10-20 | 1
Create a spreadsheet to send to Henry / allow Curators to fill in | Low Risk | Alex | 100% | 2022-10-24 | 2022-10-26 | 2
Add missing data found in figures in the article | Med Risk | David / Renuka | 0% | 2022-10-26 | 2022-11-15 | 20
Final letter Push (n = ∞)
Email POC's for review and accept | Low Risk | David / Renuka | 0% | 2022-11-04 | 2022-11-15 | 11
Final Cut off Date | Milestone | David / Renuka | 0% | 2022-11-15 | 2022-11-16 | 1 | bar: 2022-11-15
QA/QC all new uploads (n~30)
Update script | High Risk | Alex | 0% | 2022-10-24 | 2022-10-31 | 7
Validate studies in ImmPort | High Risk | Alex | 0% | 2022-11-07 | 2022-11-20 | 13
Upload all studies | Med Risk | Alex | 0% | 2022-11-10 | 2022-11-25 | 15
QA / QC studies in DR46 | Low Risk | David / Renuka | 0% | 2022-11-15 | 2022-11-30 | 15
To add more data, Insert new rows ABOVE this one
Formulas:
Legend: = DAYS(Milestones43524[[#This Row],[1 Day Before Due Date]],Milestones43524[[#This Row],[Start]])

## DecisionLog
Decision Log
Project Name
Program Manager
Date | Decision Details | Approved/Agreed By | Comments